Season-long Calendar for Agro-pastoral Field School (APFS) - Local Chicken (Indigenous Poultry) | JULY 2025

| Session | MAB | LGS | Topic | Objectives | Content | Field Activities | Materials |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | - | - | Meeting sub-county leadership and technical staff | Create awareness of Poultry FFS and seek support | FFS methodology, expected benefits, stakeholder involvement | Introductory meeting, stakeholder identification | Introductory letter, FFS brochures |
| 2 | - | - | Meeting parish leadership and committees (LCs, PDCs) | Sensitize leaders, clarify roles | APFS methodology, community roles | Planning community sensitization | FFS brochures |
| 3 | - | - | Community sensitization | Raise interest in Poultry FFS | Benefits, roles, commitment needed | Awareness meeting, fix enrollment date | Stationery |
| 4 | - | - | Participant identification and enrollment | Identify interested poultry keepers | Characteristics of participants, comparison with other approaches | Register participants, schedule group formation | Stationery |
| 5 | - | - | Group formation | Form learning groups with shared interest | Membership criteria, gender mainstreaming, norms | Develop group name, mini-teams, constitution | Sample constitution/guidelines |
| 6 | - | - | Group formalization | Structure the group and its systems | Leadership, records, group savings, bank account | Leader election, savings mobilization | Registration checklist |
| 7 | - | - | Farming as a business | Promote poultry as an enterprise | Cost-benefit analysis, enterprise selection | Profitability analysis of poultry | Enterprise templates |
| 8 | - | - | Group action plan development | Develop seasonal poultry activity plan | Problem-solution analysis, enterprise planning | Action plan drafting | Planning cards |
| 9 | - | - | Learning schedule development | Align learning to poultry cycle | Chick, grower, layer stages | Build group poultry lifecycle calendar | Lifecycle charts |
| 10 | - | - | Chick management | Improve brooder care and chick survival | Brooding, vaccinations, chick feeding | Construct a demo brooder | Charcoal stove, brooder samples |
| 11 | - | - | Grower management | Support growth and parasite control | Housing, deworming, health practices | House inspection, deworming demo | Dewormers, housing model |
| 12 | - | - | Layer and broody hen care | Improve egg production and brooding | Nest hygiene, calcium needs, egg handling | Egg collection, biosecurity practice | Nest boxes, supplements |
| 13 | - | - | Disease prevention | Enhance poultry health and biosecurity | Common diseases (Newcastle, AI), vaccinations | Poultry scouting | Vaccine samples, posters |
| 14 | - | - | Parasite control | Manage external and internal parasites | Worms, lice, mites, treatment methods | Dusting and sanitation demonstration | Dusting powder, sprayers |
| 15 | - | - | Poultry housing | Promote improved shelter designs | Low-cost, ventilated, safe housing | Poultry shelter construction | Timber, wire mesh |
| 16 | - | - | Poultry nutrition | Ensure balanced feeding across stages | Feed types and local formulation | Feed mixing demonstration | Feed ingredients, containers |
| 17 | - | - | Poultry marketing and value addition | Maximize income from poultry | Egg marketing, packaging, market links | Market survey and role play | Sample packaging, market list |
| 18 | - | - | Graduation | Celebrate achievements, encourage sustainability | Impact review, member testimonies | Presentation, role plays, certificate award | Certificates, caps, T-shirts |

Include post graduation activities, including Vachain Developement ?

download in word