Season-long Calendar for Agro pastoral Field School _ JULY 2025

| Session | MAB | LGS | Topic | Objectives | Content | Field activities | Materials |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | - | - | Meeting the sub-county leadership and technical staffs | - To create awareness on APFS, seeking their views and approval of the program | - Methodology of the implementation - Their level of involvement and that of the community and possible benefits | - Introduction - Stakeholder identification - Identification of other development partners; what they doing, how and for how long. | - Introductory letter from the organization - APFS brochures |
| 2 | - | - | Meeting parish leadership and respective committees (LCs, PDCs) | - To create awareness of the APFS approach. - Spell out level of their involvement - Mobilization for community sensitization and awareness meetings | - Overview of APFS methodology - Leaders and community roles in the APFS approach | - Briefing the parish leadership on APFS approach - Making program for community awareness meeting | - APFS brochures |
| 3 | - | - | Community sensitization | - To create awareness of the APFS approach - Arouse interest among potential APFS | - Overview of APFS methodology. - Level of community involvement. | - Holding an awareness meeting - Fixing date for follow up meeting | - Stationery |
| 4 | - | - | Follow up | - To meet and identify interested and potential APFS participants | - What is an APFS approach - Basic concepts of a APFS - Requirements of an APFS | - Enrolment of interested participants - Comparison of APFS with other approaches - Fixing date for group formation meeting | - Stationery - |
| 5 | - | - | Group formation | - To come up with list of participants with a common interest and willing to learn together | - Criteria for APFS membership - Mainstreaming gender in the APFS - Group constitution and norms, Leadership | - Formation of group name and slogan - Developing group norms - Formation of mini-groups (host teams) - Initiate the developing of group bylaws and constitution | - Sample of a APFS constitution/ guidelines |
| 6 | - | - | Group formalization | - To streamline group structure | - Leadership structure - Group dynamics - Record keeping - Savings mechanism - Group registration - Joint Group bank accounts | - Election of leaders & stipulation of their roles and responsibilities - Mobilization of funds from APFS members for registration and account opening | - List of requirements for registration and opening up of group bank accounts |
| 7 | - | - | Farming as a business | - To orient farmers to appreciate their farming enterprises as business entities | - Enterprise selection | - Establish the profitability of some of the common crops grown in the community | - -Samples of tools required |
| 8 | - | - | Development of group action plan | - To develop group action plan | - Problem identification and analysis - Problem – solution analysis - Solution assessment | - Enterprise selection | - Samples of tools required |
| 9 | - | - | Development of learning program | - To develop a schedule of learning activities that is tailored to the enterprise production cycle | - livestock cycle | - Developing livestock cycle of selected enterprise e.g Goats | Study materials for Goats lifecycle |
| 10 | - | - | Agreeing on the animals to be tagged for study purpose | - Selecting 2-3 animals to enable the group carry out study on | - Indicators healthy and sick animals - Housing conditions | - Observation - Heard health conditions | - thermometer |
| 11 | - | -- | Understanding herd health and management practices | - To appreciate key management practices in animal health management | - Concept of a healthy animals - E.g. Management of in kid goats - Housing | - Different housing designs - Isolation of in kid goats - Setting and constructing a goats houses suitable for pregnant and those that have given birth | - Timber and other building materials |
| 12 | 1 |  | Introduction to ecological relationships | - To enable farmers appreciate the interaction between the crops and other organisms in the ecosystem to guide in making off appropriate management decisions | - Ecosystem (ecological relationships) - Life cycle - Food chain - Food web | - Constructing a simple food chain and food web | - Roll of knitting thread - Manila cards |
| 13 | 2 |  | Introduction to PESA | - To enable farmers to carryout - Agro Ecosystem Analysis (PESA) | - 4-stage process of PESA - Developing parameters to observe - PESA data sheet - PESA presentation format | - Demonstrate the entire process of PESA | - Flip charts and markers - Note books - Crayons - Pencils |
| 14 | 2 |  | Conducting PESA | - To enable farmers carry out critical observations on relationships among insects in the field and the plants | - What is a Pest and a Natural Enemy - Insect zoo | - Collection of insect samples - Characterising insects to parasites and Natural Enemies - Making of insect zoos and boxes | - Manila cards, Rulers, Spirits - Staples & staples |
| 15 | 3 |  | - Identification of common parasites and diseases of Goats - Introduction to IPPE(Integrated production participatory epidemiology) | - To acquaint farmers familiar with common parasites and diseases of Maize - To acquaint farmers with the different practices of IPPE | - Common livestock parasites and diseases and their effects - Management of parasites and disease - Application of IPPE on Goats production | - Identifying common parasites and diseases of Goats - Identifying common parasites. . | - Sample of different types of parasites ( Endo and Ecto Parasites |
| 16 | 5 |  | Kid management | - To enable farmers appreciate the different management practices in Kid management | - Effects of orf in kids. - Diarrhoea in Kids - Methods of disease control | - Identification of common parasites and diseases in Kids - Trapping various parasites that affect the kids and their mothers | - Samples of parasites |
| 1 | 6 |  | Safe use of Agro-chemicals | - To enable farmers understand the safe use of livestock drugs | - Safety precaution to be observed before, while using and after spraying of animals - Accaricides mixing | - Identifying common accaricides in the market - Demonstration of calibration, direction of spraying and handling of spray pumps | - Common accaricides formulations - Bucket pump. - Water |
| 20 | 7 |  |  |  |  |  |  |
| 21 | 8 |  | Basic principles of nutrition | - To create awareness on the importance and basic principles of nutrition in a household | - Importance of vitamin, proteins and carbohydrates in our diet - Feeding for school going children - Feeding for breast feeding mothers - Feeding for the sick | - Preparation of some of the nutritious recipes | - Samples - Transport |
| 22 | 10 |  |  |  |  |  |  |
| 23 | 11 |  | Kid management | - To ensure faster health growth of the Kid | - Parasites and disease control | - House hygiene | - Rakes and wheel barrow other containers |
| 24 | 12 |  | Water and sanitation | - To ensure good sanitation in APFS community. | - Proper waste disposal - Protection of water sources - Household hygiene - Solid waste management | - Construction of drying racks, bath shelters, pit latrines and rubbish pits. - Cleaning and protecting water points. | - Stationery - Transport - Farm tools |
| 25 | 13 |  | Animal Husbandry Practices | - To ensure proper growth and development | - parasites and disease identification - Parasites and disease control | - Early detection through observation | - Note books |
| 26 | 14 |  | Principles of rangeland management | - To create awareness on need for sustainable rangeland management | - Afforestation-fodder trees - Agroforestry-wood lots - Protection of wet lands and Water sources - Energy saving structures | - Guidance by environment subject matter specialist. | - Stationery - Facilitation allowance - Transport |
| 27 | 15 |  | HIV/AIDS | - To create awareness on effect of HIV/AIDS on agricultural production and how it can be mitigated | - Impact of HIV/AIDS on farm production. - Voluntary counselling and testing. | - Brainstorming on various experiences | - Stationery - Transport - Facilitation allowance |
| 28 | 16 |  | Weaning stage | - To observe proper performance of the kid | - Proper feeds for the weaners | - Demonstration on how to make weaner feeds | - Different feed materials - Containers |
| 29 | 17 |  | Field day | - Increasing community awareness of the APFS approach | - Relating the field activities and farmers knowledge attained to empowerment | - Speeches - Presentations by APFS members - Role plays - Sharing of experiences. - Visiting the study sites | Hand-outs |
| 29 | 18 |  | Worms in Animals | - To enable farmers identify worms - To come up with control and management measures | - Signs and symptoms of worms | - De worming - Observation of possible signs & symptoms of parasites and disease | - Stationary - Pictures of worm infested animals |
| 30 | 25 |  | Ticks in Animals | - To ensure proper control of ticks | - Common sites of tick infestation - Methods of control - Importance of routine spraying. | - Observation done- | Samples of common livestock drugs used to control ticks |
| 31 | 26 |  | Signs of heat in Goats | - To enable farmers identify signs of heat in Goats | - Heat signs | - Observation of female goats signs | - Pictorials |
| 32 | 27 |  | Steaming in Animals | - To enable farmers carryout proper and timely steaming of goats | - Feed types needed for steaming in Goat management | - Observation continued | - History of the Goats |
| 33 | 28 | - | management of pregnant goats | to enable farmers appreciate key challenges during pregnancy | pregnancy indicators | observation | - Pictorials |
| 34 |  |  | First trimester issues | - To enable herders understand common issues during the first trimester | - Weight gain - Estimating weight | - Restraining to take weight | - All the records |
| 35 |  |  | Feeds during the first trimester | - To enable farmers understand the suitable feeds during the first trimester | - Different feeds and preparation and supplementary feeds | - Feed materials gathering |  |
| 36 |  |  | Pasture production | - To enable farmers raise suitable pasture for pregnant animals | - Samples of good pasture - Hay and silage making | - Look for materials of good pasture establishment | - Hay bailer |
| 37 |  |  | Zoonotic disease | - To enable Herders understand the common zoonotic disease | - Outline of common zoonotic diseases | - Identification of affected animals | - PESA |
| 38 |  |  | Second trimester issues | - To enable herders understand common issues during the second trimester | - Weight gain - Estimating weight - Heart beat checks | - Restraining to take weight | - Stesticope - Girth tape |
| 39 |  |  | Third trimester | - To enable herders understand common issues during the third trimester | - Weight gain - Estimating weight - Heart beat checks | - Restraining to take weight - Statoscope | - Stestecope - Girth tape |
| 40 |  |  | Delivery preparation | - To enable herders prepare in advance the necessary things to be used at the time of delivery and other issues | - Housing - Umbilical treatment - Colostrum use | - Treatment of affected animals | - Tincture of iodine |
| 41 |  | - | Graduation | - To reorganise and express appreciation to the perseverance of the farmers | - Testimonies from grandaunts - Reviewing the benefit and challenges in the implementation of the APFS | - Sharing experiences - Role plays - Coming up with recommendation for the future implementation of APFS. - Giving certificates to APFS members. | - T/shirts? - Caps? - Certificates |
| 42 |  | - | Post-graduation activity | - To enable the facilitator formally exit the direct the running of APFS activities | - Sustainability of the APFS group and follow up | - Mapping out follow up strategies. - The facilitator formally exits the direct running of APFS |  |

Materials other than the obvious ones like stationary, transport etc